## Slide 1: Monitoring and Evaluation Frameworks
What is an M&E Framework?
Why do we use M&E Frameworks?
How do we develop M&E Frameworks?

## Slide 2: M&E Frameworks
Models, pictures or maps
Visualize the factors that drive an intervention
Maps that illustrate how a program should work
Identify relationships between factors that influence program operation and the successful achievement of objectives
Notes: Frameworks are borrowed from the social sciences.
Helpful tool for planning programs, specific interventions, research, and M&E.
Helps us see what is contributing to challenges and successes.
Relationships can be synergistic or sometimes represent obstacles to our success.
***Key relationship that affects success of NTPs in this region is the clinical and epidemiological relationship between TB and HIV.
***Another example is health sector reform – can visualize how these changes will affect program with a framework and plan for anticipated challenges.

## Slide 3: Why do we use M&E frameworks?
Communication and planning tool
As a ‘map’ for program goals
Links between resources and activities
Guide selection of indicators
Notes: Purposes:
Clarify assumptions, goals, and interrelationships among factors relevant to the project or program
Define levels of performance and desired results in terms of planned activities and realistic, objective impacts
Monitoring and evaluation frameworks incorporate:
Program managers’ assumptions and objectives, in a given context
Schematic design displaying the directional linkages between key program elements and/or planned results, and other relevant factors
M&E takes place at multiple stages of a program. It is important to identify at the outset how we will gather information at each level of evaluation.
Framework drives selection of indicators and reporting process.

## Slide 4: M&E LOGICAL FRAMEWORKS
Illustrate the relationships between program Inputs, Processes, Outputs, and Outcomes.
Links the program to desired Impact.
Notes: <number>
<footer>
<header>
<date/time>
Key relationship:
Inputs are necessary to create processes, which drive the production of outputs and outcomes.
Reiterates the point on the previous slide.

## Slide 5
INPUT
Resources
Clinical and managerial Staff
Drugs
Laboratories
PROCESS
Management
Communication
Advocacy
Human resources development
Surveillance system
OUTPUT
Diagnostic services
Treatment services
Knowledge
Reduced Stigma
OUTCOME
Case detection
Case treatment
Case holding
IMPACT
TB infection
TB morbidity
TB mortality
CONTEXT
Political commitment Health system Socio-economic conditions Epi-context
Availability HIV prevalence
Access Malnutrition
Utilization Alcoholism
M&E logical framework for TB programme
Notes: Here is a generic example of an M&E framework for a national TB program. This framework shows the linear relationships between inputs, processes, outputs, outcomes, and impact. It also provides a visual interpretation of the broad context for the NTP, which includes: Political commitment
Health-system variables
Socio-economic conditions
Epidemiological context of TB

## Slide 6
INPUT
Drugs
Guidelines for DOT
Human Resources
PROCESS
Training of HCWs
Distribution of drugs
Supervision
OUTPUT
HCWs trained to provide DOT
Drugs available at facilities
Patients receiving DOT
Treatment outcomes reported
OUTCOME
Improved cure and treatment completion rates
Decreased failure and default rates
IMPACT
Reduced morbidity/ mortality due to TB
Prevention of MDR TB
Logic Framework example:
Directly Observed Therapy
Notes: Idea is to expand on it and create a M&E logical framework that could be used to guide planning, monitoring and evaluating the introduction of directly observed therapy as the standard of care for smear positive TB cases.

## Slide 7: Logic Framework
Input  Process Output  Outcome  Impact
Program Level (cohort) Population level
Notes: <number>
<footer>
<header>
<date/time>
Another way to understand frameworks – think about the level of measurement.

## Slide 8: Conclusions
Which program components should be monitored?
Strategic and systematic planning of M&E
Appropriate methodology for M&E activities
Indicator selection
Notes: <number>
<footer>
<header>
<date/time>
Conclusions about M&E frameworks Frameworks allow Program Manager Decide on what elements to monitor Plan strategically for M&E activities Choose appropriate methodology for M&E Select indicators to monitor and evaluation program implementation

## Slide 9: Haba na haba, hujaza kibaba.
-Swahili kanga writing
Little and little,
fills the measure.
Notes: Small things, when combined together, make up big things. All these inputs, processes, outputs, and outcomes lead to the ultimate impact of reduced morbidity and mortality associated with TB. None of them is enough to achieve the goal. A framework helps us to see how they work together and to guide us in monitoring and evaluating these components.