## Slide 1: Comprehensive M&E Systems
Identifying Resources to Support Monitoring & Evaluation Plans for National TB Programs

## Slide 2: Objectives of Session
Identify the key elements of a comprehensive M&E system
Identify importance and objectives of an M&E system
Describe key steps to strengthening or establishing and M&E system

## Slide 3: Key Elements of an M&E System
M&E management
Linked to program/strategy goals and objectives
Indicators
Data collection systems
Data analysis, use & dissemination plans

## Slide 4: Information Continuum
Notes: Show a continuum of data demand, generation, collection and use
activities. This continuum is cyclical, reflecting an ongoing, iterative process. Partners work to ensure that data users demand quality data and that data producers understand users’
priorities and information needs.

## Slide 5: How can a comprehensive M&E system support the NTP?
Efficient use of data and resources
Responsive to key stakeholders
Guarantee that donor funded M&E efforts contribute to national needs
Encourage communication between all those responsible for addressing TB
Notes: With strong M&E system you can ensure that indicators and methodologies are comparable over time and reduce duplication of effort. Particularly important where resources are scarce.
NTP often need to report to various constituents (program managers, politicians, donors, researchers, etc…)
Rather than simply serving the reporting needs of agencies or legislatures overseas
Lab, nurses, community outreach, etc… requires shared planning, coordination execution and analysis, or data dissemination

## Slide 6: Objectives of an M&E system
Measure progress
Improve accountability and management of resources
Efficiently and effectively use data
Improve coordination with partners
Collect complete and timely information on national effort to control tuberculosis

## Slide 7: Steps to strengthen and implement an M&E System
1.) M&E Situation Analysis
2.) Develop M&E plan
3.) Establish/Strengthen M&E Unit
4.) Implementation of M&E Plan
5.) Mechanisms for Management and Quality Control of M&E Activities
Notes: <number>
<footer>
<header>
<date/time>
We have already done 1. and 2. and this presentation and following group activity will focus on 3 and 4.

## Slide 8: Step 1: M&E Situation Analysis
Objectives:
  Identify existing M&E practices, indicators, and data sources already being collected
  Identify gaps where indicators will need to be developed and data sources identified for the M&E plan of the national TB program
  Assess national M&E capacity and needs for capacity development
  Identify potential for integration of TB M&E into national HIS
Notes: <number>
<footer>
<header>
<date/time>
Review this quickly

## Slide 9: Step 1: M&E Situation Analysis
Methodology
  Desk review: essential documents
  Structured interviews with national level stakeholders
  Structured interviews with regional and district level stakeholders, including community organizations
  Structured interviews with data users at all levels
Notes: <number>
<footer>
<header>
<date/time>
Needed?

## Slide 10: Step 2: Develop M&E plan
Develop clear goals and objectives to meet challenges
Propose interventions
Select and/or develop indicators to measure interventions
Identify data sources and ensure collection is feasible
Identify those responsible for data analysis, use and dissemination
Notes: <number>
<footer>
<header>
<date/time>
Using the M&E framework…
This is what we did this morning

## Slide 11: Step 3: Establish/Strengthen M&E Unit
Unit within the NTP or implementing organization
Ensure adequate financial resources
Strengthen human capacity
Ensure regular supervision of data collection and reporting
Notes: <number>
<footer>
<header>
<date/time>
Financial resources
- Budget of 5-7% of grant proposal
- If within NTP, significant government contribution
Human resources
- M&E expertise leading and involved in the unit (program monitoring, information systems, epidemiology, statistics, data processing, and social science)
- Involvement of academia (epidemiology, social sciences, communication)
Involvement of key NGOs, donors and international organizations
*It is essential to work within the existing system and unit

## Slide 12: Step 4: Implementation of M&E Plan
Develop strategy to build and maintain M&E capacity at national and sub-national levels
Adapt forms and guidelines for M&E at different levels
Coordinate with sub-national, national and international M&E experts to support implementation of plan
Training of staff at different levels
Develop guidelines for reporting requirements
Notes: <number>
<footer>
<header>
<date/time>

## Slide 13: Step 5: Mechanisms for Management and Quality Control of M&E Activities
If necessary, adapt national data base for indicators and report generation
Carry out regular assessments of quality of M&E reporting at district (and regional) level and sectors (bi-annual system, each year half of the districts)
Carry out regular assessments of quality of program monitoring
Establish feedback mechanisms!
Notes: <number>
<footer>
<header>
<date/time>

## Slide 14: M&E System Costs
Rule of Thumb is 10% of program budget (GFATM says 5-7%)
- Situation Analysis and Design of M&E plan for proposal
- Strengthening of M&E unit
- Routine Data Collection
- Data Management and Reporting
- Build capacity for analysis and use of data
- Quality Control Improvements
- Special surveys

## Slide 15: Priorities for M&E Systems Development and Strengthening
- Who will implement the system?
- How will the data be collected?
- How will the data be analyzed and used?
- How will the quality be ensured?
Notes: <number>
<footer>
<header>
<date/time>
If there is good M&E plan in the proposal, it should be able to answer all of these questions.

## Slide 16: Checklist of Good M&E System
M&E UNIT
A unit or individual within the central unit of the program who is responsible for M&E A significant contribution to the national M&E budget A formalized (M&E) link with national and local research institutions, professional associations, and academic institutions A formalized (M&E) link with leading NGOs, donors, and community-based organizations Epidemiologist and/or social science expertise in the M&E unit or affiliated with the unit Data processing and statistical expertise in the M&E unit or affiliated with the unit Data dissemination expertise in the M&E unit or affiliated with the unit
Clear Goals
Well-defined national program goals and targets Regular reviews/evaluations of the progress of the implementation of the national program plans Guidelines and guidance to districts and regions or provinces for M&E Guidelines for linking M&E to other sectors Coordination of national and donor M&E needs
Indicators
A set of priority indicators and additional indicators at different levels of M&E, some of which are comparable over time and with other countries
Data Collection, Analysis, and Use
An overall national data collection and analysis plan A plan to collect data and analyze indicators at different levels of M&E Systemwide knowledge and capacity (e.g., tools and budget) to collect and use data A plan to supervise, support, and ensure the quality of data collection A plan to ensure the translation of data into problem identification, strategic planning, policy formulation, etc.
Data Dissemination
An overall national data dissemination plan A well-disseminated informative annual report of the M&E unit Annual meeting to disseminate and discuss M&E and research findings with policy-makers and planners A clearinghouse for generation and dissemination of findings A centralized database or library of all data collection, including ongoing research Coordination of national and donor M&E dissemination needs
Notes: Run through this and pass out handout of this. Explain that the next group activity will be using this as a point of discussion to asses own M&E system

## Slide 17: Lessons learned from successful M&E Systems
Collect complete input and output data
Requires internal self-assessment and external evaluation
System should be a simple as possible
Standardized core set of tools to collect and analyze data
Human capacity to collect, verify, enter and analyze data
M&E system built into the design of the program
Sub-national data important for national level and even more so for program management and decision making
Source: GFATM Tool Kit

## Slide 18: Resources
GFATM (2004). Monitoring and Evaluation Toolkit HIV/AIDS, Tuberculosis and Malaria
WHO (2004). Global Tuberculosis Control: Surveillance, Planning, Financing. WHO Report 2004.
WHO/IUATLD (2005). Anti-TB Drug Resistance Surveillance in the World. Report No. 3.
WHO (2004). Compendium of Indicators for Monitoring and Evaluating National Tuberculosis Programs.
WHO (1998). Tuberculosis Handbook.
SWEF Research Network (2003). Common Research Protocol. Monitoring and Evaluating the Health System-wide Effects of the Global Fund to Fight AIDS, Tuberculosis and Malaria.
PHRPlus (2003). The System Wide Effects of The Global Fund : A Conceptual Framework
Econ Analysis (2005). Inventory of M&E practices and systems for global health organizations.